## Project Timeline
PROJECT TIMELINE - Gruppe 16:
Enter the date of the first Monday of each month ---->
| SEPTEMBER | [8 empty] | OKTOBER | [7 empty] | NOVEMBER | [8 empty] | DECEMBER
| 1 | 6 | 8 | 13 | 15 | 20 | 22 | 27 | 29 | 4 | 6 | 11 | 13 | 18 | 20 | 25 | 27 | 1 | 3 | 8 | 10 | 15 | 17 | 22 | 24 | 29 | 1 | 6 | 8 | 13 | 15 | 20 | 22
PROJECT WEEK |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51
ITERATION#1
Probelmformulering
ITERATION#2
Kravspecifikationer, system-arkitektur og acceptest
ITERATION#3
Afdækning af risici og tidlig implementering
ITERATION#4
Konstruktion
ITERATION#5
Afslutning af projekt
Problemformulering
Systembeskrivelse
MoSCoW
Use cases
Software arkitektur
Afdækning af risici (punkter)
Acceptest
FURPS
For-sensor
Batterisensor
Motorer til baghjul
Integration
Test
Rapportskrivning
Ikke-funktionelle krav
Hardware arkitektur
Dyse
Karosseri
Opfølgning på feedback
Brugergrænseflade
For-sensor-styring
Dyse
Brugergrænseflade
Præsentation

## BLANK - Project Timeline
PROJECT TIMELINE
Enter the date of the first Monday of each month ----> | Q1 | [14 empty] | Q2 | [13 empty] | Q3 | [12 empty] | Q4
| JANUARY |  |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER
| 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 34 | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25
PROJECT WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PHASE ONE
Project Conception and Initiation
PHASE TWO
Project Definition and Planning
PHASE THREE
Project Launch of Execution
PHASE FOUR
Project Performance and Control
PHASE FIVE
Project Close
TODAY
Project Charter
Plan Review
Initiation
Scope & Goal Setting
Budget
Work Bkdwn Structure
Gantt Chart
Communication Plan
Risk Management
Forecasts
Quality
KPIs
Status and Tracking
Objective Execution
Quality Deliverables
Effort & Cost Tracking
Performance
Post Mortem
Project Punchlist
Report
PROJECT END